## Tabelle1
|  | Transport Disruptions Tina Bessel | ATMO prediction system Bernhard Mühr | Crowd Sorucing Joachim Fohringer / Christian Lucas / André Dittrich | Rapid Flood Event Analysis in Germany Kai Schröter | Causal Loss Assessment - Shelter Needs Susan Brink / Bijan Khazai | Real-Time Evaluation of Disaster Management System Response Trevor Girard | Case Based Reasoning CBR Stella Möhrle | Slip distribution Andreas Höchner | Business and supply chain interruptions Hanns-Maximilian Schmidt
Product |  | Loss assessment Model | Storm Damage Model | Information System from Social Media | Model for damage estimation | Model for shelter / displacement | Evaluation model for Disaster Manag. | data base, event assessment | Methodology for earthquake source inversion | Input-output based model for loss estimation
Area |  | Germany | Germany / Europe | worldwide | Germany | worldwide | worldwide | worldwide | Subduction zones worldwide (given data) | Germany (/ Europe)
Event type |  | flood, storm | winterstorm | all | flood | earthquake, flood, storm, hail | all natural disasters | storm, flood, earthquake | Earthquake / Tsunami | all
Expected Results Project | 12/2013 | Development of framework/concept to assess transport disruptions during flood (June 2013, Germany) | # Data base of events complete # Gathering and calculation of damage to quantify a storm damage index | # identification of non-textual Information from Twitter # first assessment of relevance of Twitter messages | Conceptual design of flood event analysis system | # Data Base established (earthquake events) # Model for number of displaced persons available | # Concept development for 8 test cases # operational scheme available | # Further programming of the CBR application # Integration of first similarity functions # Planning of the future Webinterface | Development of time dependent source description and inversion technique | ---
| 06/2014 | Development of a model for fast loss assessment in the transport sector | # Validation of storm data index, storm damage index with storm forecast data, damage function # Wind gust parametrization # Online implementation | Interactive prototype to explore Twitter-messages (text and photos) during ongoing catastrophes | # Flood event catalogue # Operational interfaces to data sources | # influence factors determined # links to shelter needs model established | # integration of more test cases # Stakeholder interaction: (USAID) #Paper submitted | # Integration of storm events # Integration of further data (e.g. location specific data) # Further programming of CBR application # Integration of all basic similarity functions | Implementation and assessment of wave form inversion | # literature review # assessment of existing models # development of the basic framework
| 12/2014 | Elaboration of a model for fast loss assessment in the transport sector | # Routine Damage estimation before , during and after storm event # Use of ensemble forecast | # autmoated classification and criteria of messages related to their content | Test and evaluation of the event analysis system | # Data Base established (floods, storm, hail events) # Model for number of displaced persons available | # expanded version developed # integration in CBR | # Complete implementation of the CBR application # Query of similar historic events via Webinterface | # Sensitivity analysis and probabilistic tsunami hazard assessment for selected regions # Linking with ground motion modeling | # application to industrial centers all over Germany # using historical data for validation
Contribution for FDA | 12/2013 | provision of information on transport disruptions as situation report |  | provision of information (text, photos) to estimate the impact of a specific katastrophe | # Spatial picture of flood hazard distribution # Classify/describe flood hazard event in respect to historical event set |  | test of the system / methodology | Research of disaster response related data | # Slip distribution estimate (for large events and data availability) # Surface deformation # Tsunami wave height prediction # Compilation of tectonic background | ---
| 06/2014 | Model for fast loss assessment in the transport sector available | Storm damage model for Germany / Europe based on deterministic forecast | provision of relevant, geo-referenced photos that allow an estimation of water levels during a flood event | Rapid flood loss estimation using data from comparable past events | predicition of number and reasons for displaced persons | system / methodology fully operational | Query of similar historic dark red earthquake and storm events | Cover broader range of events by integration of accelerometer data | # fast identification of key industries within the affected regions # assessment of overall economic losses (indirect losses)
| 12/2014 | further improved model available | Probabilistic storm damage model for Germany / Europe based on probabilistic forecast | provision of information about intensity and impact of a catastrophe derived from classified and geo-referenced Twitter messages (teext, photos, maps) | Rapid flood loss estimation for residential buildings using flood loss models | predicition of shelter needs in earthquake | system / methodology fully operational | Complete use of CBR application for FDA activity | Peak ground acceleration | # operational tool for a fast assessment of industrial losses # further improvements